Plans for the Global Warming Cafe

Date: 		January 30, 2016

Time: 		7:00 – 9:30 p.m. (Set-up 6:00 -7:00; clean-up 9:30 – 10:00)

Place: 		First Unitarian Universalist Society of Marietta (232 Third St., Mtta, OH)

Fellowship Hall (basement)

Hosted by: 	MOV Climate Action Group (or whatever the name is)

Low Carbon Diet Team

Green Sanctuary of FUUSM

Done by	Task

Jan. 12		Send invitations by email (I will have the E-invite ready by Thursday)

NOT TOO LATE to send to others or to those suggested if you haven't done so already.

    - Adeline and Mike Bailey send to Green Sanctuary/FUUSM, ARECC, FLMR, Fracking interest group, friends and family

    - Dawn Hewitt send to Marietta College science faculty and environmental groups, Natural History Society, friends and family

    - Wayne Dunn send to Baha'i friends

    - Wendy Tuck (and/or Cindy Taylor) send to Quakers, friends, family

    - Eric Engle (and/or Rebecca Phillips) send to WVU-Parkersburg groups, friends, family

    - Bill and Jean Ambrose send to CCL and Facebook

    - Mark Redd send to Low Carbon Diet groups

    - Others?

Jan. 24		Follow up on invites via phone if possible

Jan. 15		Post invitations at libraries (?) and colleges

- Wood County

- Washington County

-  WVUP - Phillips

-  WSCC

-  Marietta College - Hewitt

Jan. 30		Get supplies and set-up stuff

- Flip charts (need 2)  Dawn Hewitt and Jean Ambrose.

- Jean will also bring legal pads for each table

- Card Tables (need 10) Baileys-3; Hewitt - 2;  Wendy Tuck – 1; Dave Ballantyne -1; STILL  NEED 3 CARD TABLES

- Table cloths for card tables (need 10) Baileys – 2; Hewitt – 2; Brad Bond - ?; Heather Royer – fabric pieces.

- Markers (need 5-6 per table in variety of colors; water based so they won't bleed through paper—NOT Sharpies)Tuck – 3 sets; Bailey – 1 set; Cindy Taylor - $20 donation for purchase of more.

- Snacks enough for 40 – 50 people; some sweet and some savory. Baileys- savory snacks; Rebecca Phillips – cookies; Carol Sedgwick – cookies; Jean Ambrose – cookies; Joan Coffey – cookies?; Karen Foss – muffins; Sister Molly donated $40 to purchase additional food items.

- Coffee – Dawn Hewitt volunteered to supply

- Tea – Baileys will contribute

- Cream, sugar, etc. Baileys will contribute

- Tape, stapler - Baileys

- Nametags - Ambrose

- Index cards - Baileys

Jan. 30		Cafe enhancements

- Welcome poster 11x 17 or larger to fit on easel/stand Still need this

- Outside Sign directing people to basement room Still need this.

- Computer setup to play music during welcome – Mike Bailey

- Votive candles for each table – Adeline Bailey

-  Videos of positive change or activities (Peoples Climate March, CCL activism?, Earth Day, Earth Hour  - Baileys are looking into this

Jan. 30		Setup  6:00 – 7:00 p.m.

Volunteeers to date: Tuck, Ballantyne, Gary Thompson, Phillips, Ambrose, Coffey, Baileys, Hewitt

Tables , cloths, paper markers, candles

Music and videos for welcome

Snack and drink buffet and people assigned to tend it

“Presenters” table (small static displays with sign-up sheets for those who 		are interested in more info or contact. Will need someone responsible for 		answering questions during welcome and breaks.

Jan. 24		Contact “Presenters”

Green Sanctuary, ARECC, MOVCA, LCD, 	FLMR , Others?

Jan. 30		Welcome table

Surveys and collection box, pens, etc. - Dave Ballantyne?

Welcome poster

Nametags

Jan. 30 	Host or hostess – Baileys

Jan. 30		Graphic recorder (if possible, words and pictures; if not, just words is OK) Still need  someone to do this—any ideas?

Jan. 30		Photographer?

Jan. 30		Cleanup Teams

Volunteers for clean-up so far: Jane Hearne, Sedgwick, Ambrose, Hewitt

Kitchen

Take down tables

Vacuum

Take down signs and charts

Check lights, doors, etc. - Mike Bailey

Optional:

Jan. 15		Publicity – MOSTLY DONE!! (Although taking some posters around, especially in Parkersburg, would be good.)

Announce on community calendars? Sent it in

Press releases, either before or after?Sent one “before”

Invitation to press people? Did not do.